## Sheet1
Sprint | Day | Impediments | Action Taken
S1 | Day 4 | Difficulty connecting Flask backend to PostgreSQL database | Installed correct drivers and updated connection string parameters
S1 | Day 9 | API response time was too high due to unoptimized queries | Added query indexing and optimized SQL joins
S2 | Day 15 | Model training pipeline failing due to version mismatch in TensorFlow | Updated TensorFlow version and retrained model with compatible libraries
S2 | Day 18 | Inconsistent loan dataset format causing preprocessing errors | Created data validation script and standardized dataset format
S3 | Day 26 | ML model accuracy was below target (70%) | Tuned hyperparameters and balanced dataset using SMOTE
S3 | Day 30 | Dashboard UI not displaying predictions properly | Fixed Flask–React integration and adjusted API response schema
S4 | Day 45 | Docker image build failing due to missing environment variables | Updated Dockerfile and .env configuration
S4 | Day 52 | Model deployment on cloud failed due to incompatible Python version | Rebuilt Docker image with correct Python version and redeployed successfully